## Sheet1
Month | Tasks | Writing
October | Reading, introduction to R coding, Data overview
November | Data preprocessing (resizing) | Concept
December | Concept presentation (17th Dec), data processing (HANTS) | Concept Presentation
January | data processing (extracting LSP Indices), preliminary LAI comparison | start Methods
February | Holidays
March | buffer | Methods, Results as they come in)
April | start work on extraced indices: Correlation coefficients, regression analysis | Results (as they come in)
May | Interpretation of trend analysis / doing/redoing statistics | finish Methods, Analysis (preliminary)
June | More time for statistics (Climatic Controls - LAI) | Analysis, start Discussion
July | holidays / buffer
August | Writing & Layouting, finishing touches | Analysis, Introduction, Discussion
September | Final Presentation, more finishing touches | more finishing touches, Thesis defense