## Timetable
Month | Tasks | Writing
October | Reading, introduction to R coding, Data overview
November | Data preprocessing (resizing) | Concept
December | Concept presentation (17th Dec), data processing (HANTS) | Concept Presentation
January | data processing (extracting LSP Indices), preliminary LAI comparison | start Methods
February | Holidays
March | buffer | Methods, Results as they come in)
April | start work on extraced indices: Correlation coefficients, regression analysis | Results (as they come in)
May | Interpretation of trend analysis / doing/redoing statistics | finish Methods, Analysis (preliminary)
June | More time for statistics (Climatic Controls - LAI) | Analysis, start Discussion
July | holidays / buffer
August | Writing & Layouting, finishing touches | Analysis, Introduction, Discussion
September | Final Presentation, more finishing touches | more finishing touches, Thesis defense

## Journal
Date | Progress | Time invested | comment
Oct 2014 | Reading papers | 30
Oct 2014 | Introduction to R coding
2014-11-01 | Reading papers | 30
2014-11-01 | R-coding simple raster operations | 24
Dec 2014 | Presentation | 14
Dec 2014 | Concept work | 18
Dec 2014 | Data preparation resizing, rotation (IDL) | 8
Dec 2014 | Data preparation layer extraction | 4
Dec 2014 | Data preparation watermask (part 1..) | 2
Dec 2014 | code LSP extraction (christmas session) | 23
Dec 2014 | HANTS extraction (getting it to work..) | 3
2014-01-01 | HANTS continued (trying out parameters) | 5
2014-01-01 | refining LSP extraction | 10
2014-02-01 | modifiying processing chain for NHEM/SHEM | 8
2014-02-01 | applying Viprocessor | 2 | BUGFIX: error when processing years without any amplitude!
Mar 14 | LAI comparison: writing bimonthly_extractor for LAIre | 3
Mar 14 | LAI comparison: difference map | 2
Mar 14 | write general correlation functions | 8
Mar 14 | rewriting watermask creation (stricter, LAI3g based) | 5 | realized when looking at correlations that many 0-values present, skewing results, especially along water-borders due to bad masking.
2014-04-01 | write decadal_change for GSL | 6 | took a while to get around NA-values...
2014-04-01 | rewrite bimonthly extractor for climatic controls | 1
2014-04-01
2015-04-24 | days_per_decade for temp-fac application | 1
2015-05-03 | Light_fac extraction, meeting preparations | 8
|  |  |  | Total | 215